6::UK
A Short History
Nigel Titley

---
Origins
- Late 2010
- BIS found £20k spare cash
- Suggested setting up an organisation to support Ipv6 rollout
- 6::UK formed

---
Mission
- To educate UK industry as to the coming shortage of Ipv4 addresses
- To instil a sense of urgency into UK industry towards adoption of IPv6
- To educate on the technical issues
- To encourage government to buy into IPv6

---
Start Up
- Classical UK non-profit membership
- Mem & Arts
- Interim Board
  - Nigel Titley, Philip Sheldrake, Peter Kirstein
- Administration
  - Jim Reid

---
High Hopes
- Launch Event
  - Vint Cerf (Keynote)
  - Good Media coverage
- Web Site
- Ministerial Meeting
  - Ed Vaisey
- Training Courses

---
Membership
- Large members
  - Easynet
- Medium members
  - AAISP, Redstone, Timico
- Small members
  - Fluid Data, Switch communications
- Academic and NFP
  - Dante, Janet, LINX, UCL
- Individual
  - Hardik Lodhiya, Tim Luck, Michard Consultancy Solutions, Mike Simkins, Kevin Taylor

---
Stagnation
- Attempts to engage industry met with no interest
  - CBI
  - Institute of Directors
  - IET
- Government thought IPv6 should be industry-led (no further funding)
- No interest in (free) training courses

---
Finance
- Income inadequate to cover further publicity
- Cut back on admin costs and ran on purely volunteer effort
- Felt it unfair to ask for more membership fees from members when so little was being delivered

---
The End
- Directors decided that with no government support (not even calling a meeting) the effort was doomed
- 2012 AGM board resigned
- Press release gained a lot of publicity
- Still no govt support
- Winding up

---
Questions?